## Graphics
Project Name: | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
Start metric date: | #REF! | Latest metric date: |  | #REF! | #REF! | Selected period: | #REF! | - | #REF! | #REF!

## Sheet1
Project Name: Personal Information Encryption
Project Manager: Salwan Luay Chasib
Test Lead: Salwan Luay chasib
| Report Date | 2019-03-25 | 2019-04-01 | 2019-04-09 | 2019-04-13 | 2019-04-22 | 2019-04-30 | 2019-05-09
| Project week number | 1 | 2 | 3 | 4 | 5 | 6 | 7
Team efforts (work-hours)
c | Total weekly efforts | 9 | 18 | 19 | 15 | 18 | 20 | 13
| Management & support | 2 | 6 | 5 | 4 | 0 | 5 | 3
| Development efforts | 5 | 9 | 10 | 8 | 14 | 11 | 7
| Testing efforts | 2 | 3 | 4 | 3 | 4 | 4 | 3
c | Total efforts SUM | 9 | 27 | 46 | 61 | 79 | 99 | 112
Lines of code
c | LOC total | 32 | 105 | 190 | 357 | 587 | 567 | 1011
| Product | 30 | 100 | 175 | 300 | 488 | 512 | 622
| Unit Tests | 2 | 5 | 15 | 57 | 99 | 55 | 389
c | Defects/(LOC/1000) | 62.5 | 28.5714 | 15.7895 | 25.2101 | 17.0358 | 26.455 | 21.7606
Bugs (numbers)
| Total Bugs | 2 | 3 | 3 | 9 | 10 | 15 | 22
| Opened Bugs | 2 | 2 | 1 | 3 | 4 | 8 | 13
c | Closed Bugs | 0 | 1 | 2 | 6 | 6 | 7 | 9
Weekly bug dynamics (numbers)
c | Weekly created | n/a | 1 | 0 | 6 | 1 | 5 | 7
c | Weekly closed | n/a | 1 | 1 | 4 | 0 | 1 | 2
Test cases (numbers)
| Planned | 1 | 2 | 2 | 3 | 3 | 2 | 1
| Total (written) | 1 | 2 | 2 | 3 | 3 | 2 | 1
| Weekly attempted | 1 | 3 | 4 | 3 | 4 | 2 | 1
| Weekly passed | 1 | 3 | 3 | 2 | 4 | 2 | 1
c | Planned - Total | 0 | 0 | 25 | 0 | 0 | 0 | 0
c | Weekly Attempted/Total (%) | 100% | 150% | 25 | 100% | 133.3% | 100% | 100%